## Template Audit
Priority Tier | Category | Asset/Template Name | Description | Format | Status | Dependencies | Deadline | Owner | Notes
1 | Logo System | Primary Logo Files (SVG, PNG, EPS, AI) | Full-color, single-color, reversed, all colorway variations | SVG/PNG/EPS/AI | Not Started |  | 2026-03-31 | Chris | All formats needed for different applications
1 | Logo System | Secondary/Alternate Mark | Secondary mark variations for constrained spaces | SVG/PNG/EPS/AI | Not Started | Primary Logo Files | 2026-03-31 | Chris
1 | Logo System | Sub-Brand Lockup Templates | Lockup templates for: Reboot, Energy Summit, Dynamist, FAI Labs, Policy Hackers, Schoolahoop, BIPBounty, Project Nickel | AI/Figma | Not Started | Primary Logo Files | 2026-05-31 | Chris | 8 sub-brand lockups needed
1 | Logo System | Logo Usage Guide Page | Page for brand book showing logo specifications, clearspace, sizing, dos/donts | PDF/InDesign | Not Started | Primary Logo Files | 2026-04-30 | Chris
1 | Logo System | Favicon & App Icon Set | 16x16, 32x32, 64x64, 128x128, 180x180 (iOS), 192x192 (Android) | PNG/ICO | Not Started | Primary Logo Files | 2026-05-31 | Chris
1 | Logo System | Watermark Versions | Semi-transparent logo for background/document watermarking | PNG/PDF | Not Started | Primary Logo Files | 2026-05-31 | Chris
1 | Color System | Color Specification Sheet | HEX, RGB, CMYK, Pantone values for primary and secondary palettes | XLSX/PDF | Not Started |  | 2026-03-31 | Chris | Include accessibility notes
1 | Color System | Color Palette Files (ASE, CLR) | Adobe Swatch Exchange and macOS/Windows color palette files | ASE/CLR | Not Started | Color Specification Sheet | 2026-04-15 | Chris
1 | Color System | Accessibility Contrast Ratio Documentation | WCAG AA/AAA compliance chart for all color combinations | PDF/XLSX | Not Started | Color Specification Sheet | 2026-04-30 | Chris
1 | Color System | Sub-Brand Color Extensions | Color palettes for each sub-brand within system | ASE/CLR/PDF | Not Started | Color Specification Sheet | 2026-05-31 | Chris
1 | Typography | Typeface License Documentation | Licensed typeface details, usage restrictions, web font rights | PDF | Not Started |  | 2026-03-15 | Chris
1 | Typography | Type Specimen Sheet | Full alphabet, numerals, punctuation in all weights/styles | PDF/InDesign | Not Started | Typeface License Documentation | 2026-03-31 | Chris
1 | Typography | Web Font Files | WOFF2 and fallback formats for web implementation | WOFF2/WOFF/TTF | Not Started | Typeface License Documentation | 2026-04-15 | Chris
1 | Typography | Typography Hierarchy Reference Card | Headline, subheading, body, caption specs with line-height and letter-spacing | PDF/XLSX | Not Started | Type Specimen Sheet | 2026-03-31 | Chris
1 | Voice & Tone | Brand Voice Guidelines | Voice characteristics, tone variations (professional, approachable, authoritative, etc.) | PDF/DOCX | Not Started |  | 2026-04-30 | Chris
1 | Voice & Tone | Boilerplate Copy Library | About paragraphs (50, 100, 150 words), mission statement, program descriptions | DOCX/PDF | Not Started | Brand Voice Guidelines | 2026-04-30 | Chris | Include variations for each sub-brand
1 | Voice & Tone | Terminology Glossary | FAI-specific terms, acronyms, preferred usage (e.g., AI, policy, tech) | XLSX/PDF | Not Started | Brand Voice Guidelines | 2026-04-30 | Chris
1 | Voice & Tone | Email Signature Standard | HTML and plain-text signature templates with logo, contact info | HTML/DOCX | Not Started | Typography;Logo System | 2026-04-15 | Chris
2 | Publications | Web-Native Policy Paper Template | HTML/CSS responsive template for publishing policy papers on website | HTML/CSS | Not Started | Typography;Color System | 2026-03-31 | Chris | High priority - March 31 deadline
2 | Publications | Print Policy Brief Template | 2-4 page InDesign template for policy briefs | INDD/PDF | Not Started | Typography;Color System;Logo System | 2026-04-30 | Chris
2 | Publications | Print Research Report Template | Multi-page InDesign template (8-20 pages typical) | INDD/PDF | Not Started | Typography;Color System;Logo System | 2026-05-31 | Chris
2 | Publications | Print Booklet/Program Template | InDesign template for event programs and booklets (Copyright Symposium, summits) | INDD/PDF | Existing/Needs Update | Typography;Logo System | 2026-02-27 | Chris | URGENT: Copyright Symposium Feb 27
2 | Publications | Blog Post Style Guide | Formatting, structure, and design specs for Sanity CMS blog posts | PDF/DOCX | Not Started | Typography;Color System | 2026-05-31 | Chris
2 | Publications | Book/Publication Cover Template | InDesign template for external and internal publications | INDD/PDF | Not Started | Typography;Color System;Logo System | 2026-06-15 | Chris
2 | Presentations | Master FAI Deck Template | PPTX and Keynote master slide templates with layouts | PPTX/KEYNOTE | Existing/Needs Update | Typography;Color System;Logo System | 2026-02-27 | Chris | URGENT: Update FAI deck Feb 27
2 | Presentations | Internal Meeting Deck Template | Simplified template for internal team presentations | PPTX/KEYNOTE | Not Started | Master FAI Deck Template | 2026-04-30 | Chris
2 | Presentations | Webinar/Virtual Event Slide Template | Template optimized for screen sharing and virtual delivery | PPTX/KEYNOTE | Not Started | Master FAI Deck Template | 2026-05-31 | Chris
2 | Presentations | Speaker One-Sheet/Bio Template | Half-page or one-page template for speaker bios with photo placement | DOCX/PDF | Not Started | Typography;Logo System | 2026-04-15 | Chris
2 | Social Media | X/Twitter Post Templates | Quote card, announcement, event promo, stat/data templates (Figma or PPTX) | FIGMA/PPTX | Not Started | Color System;Typography;Logo System | 2026-05-31 | Chris | 4 template variations
2 | Social Media | LinkedIn Post Templates | Article share, announcement, event templates (image specs) | FIGMA/PPTX | Not Started | Color System;Typography;Logo System | 2026-05-31 | Chris
2 | Social Media | YouTube Thumbnail Template | 1280x720px template with text, logo, graphics specs | FIGMA/PPTX | Not Started | Color System;Typography;Logo System | 2026-05-31 | Chris
2 | Social Media | YouTube Channel Art | 2560x1440px banner for channel header | FIGMA/PPTX | Not Started | Logo System;Color System | 2026-05-31 | Chris
2 | Social Media | Instagram Templates | 1080x1350 (feed), 1080x1920 (story), carousel specs if applicable | FIGMA/PPTX | Not Started | Color System;Typography;Logo System | 2026-05-31 | Chris
2 | Social Media | Social Media Avatar & Profile Photo Specs | Size, format, and brand guidelines for profile pictures | PDF/FIGMA | Not Started | Logo System | 2026-04-15 | Chris
2 | Social Media | Podcast Cover Art Template (The Dynamist) | 3000x3000px Apple Podcasts and Spotify compliant template | FIGMA/PPTX | Not Started | Logo System;Color System | 2026-05-31 | Chris | The Dynamist sub-brand
2 | Email / Newsletter | The SCIF Newsletter Template | HTML email template with responsive design (150, 600, 800px widths) | HTML | Not Started | Typography;Color System;Logo System | 2026-04-30 | Chris | SCIF is weekly newsletter
2 | Email / Newsletter | Event Invitation Email Template | HTML email for event RSVPs with CTA buttons | HTML | Not Started | Typography;Logo System;Color System | 2026-04-30 | Chris
2 | Email / Newsletter | Fundraising/Donor Email Template | HTML template for donor appeals and campaigns | HTML | Not Started | Typography;Logo System;Color System | 2026-05-31 | Chris
2 | Email / Newsletter | Internal Announcement Email Template | HTML template for team announcements | HTML | Not Started | Typography;Logo System;Color System | 2026-04-30 | Chris
2 | Email / Newsletter | Email Signature Template | Branded HTML and plain-text signature for staff | HTML/DOCX | Not Started | Typography;Logo System | 2026-04-15 | Chris
2 | Events | Event Branding Toolkit | Master template and guide for creating event identities within brand system | PDF/INDD | Not Started | Logo System;Color System;Typography | 2026-05-31 | Chris | Framework for all events
2 | Events | Event Program/Booklet Template | Multi-page InDesign template for event programs | INDD/PDF | Not Started | Typography;Logo System;Event Branding Toolkit | 2026-04-30 | Chris | Used for summits, symposia
2 | Events | Event Signage Template Set | Podium sign, banner stand (8'x3'), directional signs, entrance sign | INDD/PDF | Not Started | Typography;Logo System;Color System | 2026-05-31 | Chris | 4-6 templates
2 | Events | Name Badge Template | Badge template with attachment options (lanyard, pin, clip) | INDD/PDF | Not Started | Typography;Logo System | 2026-04-30 | Chris
2 | Events | Event Invitation (Digital - Luma) | Luma event page design specifications | PDF/FIGMA | Not Started | Typography;Logo System;Color System | 2026-04-30 | Chris
2 | Events | Event Invitation (Print) | Postcard or folded card template for print invites | INDD/PDF | Not Started | Typography;Logo System;Color System | 2026-04-30 | Chris
2 | Events | Step-and-Repeat/Photo Backdrop Template | Branded photo backdrop specifications (8'x8' typical) | INDD/PDF | Not Started | Logo System;Color System | 2026-05-15 | Chris | For press/photography
2 | Events | Event Slide Template | PowerPoint/Keynote template for in-venue screens and transitions | PPTX/KEYNOTE | Not Started | Master FAI Deck Template | 2026-05-31 | Chris
2 | Events | Table Tent/Place Card Template | Small standing card for dining, table numbering, sponsor recognition | INDD/PDF | Not Started | Typography;Logo System | 2026-04-30 | Chris
2 | Stationery | Letterhead Template | 8.5x11" letterhead with header, footer, logo | DOCX/PDF/INDD | Not Started | Logo System;Typography;Color System | 2026-04-30 | Chris
2 | Stationery | Business Card Template | Standard 3.5x2" with full bleed | INDD/PDF | Not Started | Logo System;Typography | 2026-04-30 | Chris | Print-ready file needed
2 | Stationery | Envelope Templates | #10 (9.5x4.125") and A7 (5.25x7.25") templates | INDD/PDF | Not Started | Logo System;Typography | 2026-04-30 | Chris
2 | Stationery | Note Card/Thank You Card Template | Folded 5x7" card for thank you notes | INDD/PDF | Not Started | Logo System;Color System;Typography | 2026-04-30 | Chris
2 | Stationery | Memo Template | Branded memo pad template (half-page, full-page) | DOCX/PDF | Not Started | Typography;Logo System | 2026-04-30 | Chris
3 | Sub-Brand Guidelines | Reboot Conference Identity Package | Logo lockup, color palette, typography specs, visual system | PDF/INDD | Not Started | Logo System;Color System;Typography;Sub-Brand Lockup Templates | 2026-07-31 | Chris | Annual tech conference
3 | Sub-Brand Guidelines | Energy Imperatives Summit Identity Package | Identity, visual system, templates for summit branding | PDF/INDD | Not Started | Logo System;Color System;Typography;Sub-Brand Lockup Templates | 2026-07-31 | Chris | Policy-focused summit
3 | Sub-Brand Guidelines | The Dynamist Podcast Identity Package | Logo, color palette, cover art, social templates for podcast | PDF/FIGMA | Not Started | Logo System;Color System;Podcast Cover Art Template | 2026-06-30 | Chris | Weekly podcast sub-brand
3 | Sub-Brand Guidelines | FAI Labs Identity Package | Distinct visual identity for research/innovation lab | PDF/FIGMA | Not Started | Logo System;Color System;Typography;Sub-Brand Lockup Templates | 2026-07-31 | Chris
3 | Sub-Brand Guidelines | Policy Hackers Identity Package | Identity for fellowship program | PDF/FIGMA | Not Started | Logo System;Color System;Typography;Sub-Brand Lockup Templates | 2026-07-31 | Chris | Fellowship program branding
3 | Sub-Brand Guidelines | Sub-Brand Identity Creation Template | Template and process guide for creating future program identities | PDF/INDD | Not Started | Logo System;Color System;Typography | 2026-08-31 | Chris | Scalability framework
3 | Donor/Development Materials | Annual Report Template | Design template for year-end annual report | INDD/PDF | Not Started | Typography;Logo System;Color System | 2026-08-31 | Chris
3 | Donor/Development Materials | Donor One-Pager Template | One-page template for donor prospect overview | DOCX/PDF | Not Started | Typography;Logo System | 2026-07-31 | Chris
3 | Donor/Development Materials | Case for Support/Prospectus Template | Multi-page template for funding pitches | INDD/PDF | Not Started | Typography;Logo System;Color System | 2026-08-31 | Chris
3 | Donor/Development Materials | Grant Proposal Cover Template | Cover page for grant submissions | DOCX/PDF | Not Started | Typography;Logo System | 2026-07-31 | Chris
3 | Donor/Development Materials | Impact Report Template | Template for showcasing impact metrics and results | INDD/PDF | Not Started | Typography;Logo System;Color System | 2026-08-31 | Chris
3 | Donor/Development Materials | Thank You/Acknowledgment Letter Template | Branded template for donor thank you letters | DOCX/PDF | Not Started | Typography;Logo System | 2026-06-30 | Chris
3 | Swag & Merchandise | Sticker Designs | Logo, tagline, and sub-brand stickers (die-cut and print specs) | FIGMA/PPTX/PDF | Not Started | Logo System;Color System | 2026-08-31 | Chris | Multiple designs
3 | Swag & Merchandise | Apparel Templates | T-shirt, hoodie, and jacket design templates (front, back, sleeve) | FIGMA/PDF | Not Started | Logo System;Color System | 2026-08-31 | Chris
3 | Swag & Merchandise | Tote Bag Template | Design template for branded tote bags | FIGMA/PDF | Not Started | Logo System;Color System | 2026-08-31 | Chris
3 | Swag & Merchandise | Lapel Pin/Enamel Pin Design | Design and specs for custom enamel or lapel pins | FIGMA/PDF | Not Started | Logo System | 2026-08-31 | Chris
3 | Swag & Merchandise | Drinkware Template | Design template for mug, water bottle, coffee cup | FIGMA/PDF | Not Started | Logo System;Color System | 2026-08-31 | Chris
3 | Swag & Merchandise | Notebook/Padfolio Cover | Design template for branded notebooks and padfolios | INDD/FIGMA/PDF | Not Started | Logo System;Color System;Typography | 2026-08-31 | Chris
3 | Swag & Merchandise | Pen/Promotional Item Specs | Specifications and design guidelines for promotional items | PDF | Not Started | Logo System | 2026-08-31 | Chris
3 | Digital/Web | Website Redesign Brief | Strategy brief and design specifications for website refresh | PDF/FIGMA | Not Started | Logo System;Color System;Typography | 2026-07-31 | Chris
3 | Digital/Web | Web Component Style Guide | Living documentation of buttons, cards, forms, navigation components | HTML/PDF/FIGMA | Not Started | Typography;Color System | 2026-08-31 | Chris
3 | Digital/Web | Open Graph/Social Sharing Image Template | 1200x630px templates for social media unfurls | FIGMA/PPTX | Not Started | Logo System;Color System;Typography | 2026-07-31 | Chris
3 | Digital/Web | 404 Page Design | Custom 404 error page design | FIGMA/HTML | Not Started | Logo System;Color System;Typography | 2026-07-31 | Chris
3 | Digital/Web | Loading/Transition Animations | CSS/animation specs for loading and page transitions | HTML/CSS/PDF | Not Started | Color System | 2026-08-31 | Chris
3 | Digital/Web | QR Code Branded Template | Specifications for branded/customized QR codes | FIGMA/PDF | Not Started | Logo System;Color System | 2026-07-31 | Chris
3 | Video/Motion | Video Intro/Outro Bumper | 10-15 second branded video bumper for content | MP4/MOV/AFTER EFFECTS | Not Started | Logo System;Color System;Typography | 2026-08-31 | Chris
3 | Video/Motion | Lower Third Template | Motion graphics template for on-screen lower third graphics | AFTER EFFECTS/FIGMA | Not Started | Logo System;Color System;Typography | 2026-08-31 | Chris
3 | Video/Motion | Animated Logo | Animated version of logo for video intro/use | MP4/MOV/AFTER EFFECTS | Not Started | Logo System | 2026-08-31 | Chris
3 | Video/Motion | Motion Graphics Style Guide | Guidelines for animation, transitions, effects consistency | PDF/FIGMA | Not Started | Color System;Typography | 2026-08-31 | Chris
3 | Video/Motion | Podcast Video Template | Video template for podcast episodes (if video content planned) | AFTER EFFECTS/FIGMA | Not Started | Logo System;Color System;Typography | 2026-08-31 | Chris
3 | Governance | Brand Approval Request Form | Form for requesting brand usage approval for new initiatives | XLSX/PDF | Not Started | Voice & Tone | 2026-06-30 | Chris
3 | Governance | New Sub-Brand Proposal Template | Template for proposing new sub-brand or program identity | DOCX/PDF | Not Started | Brand Voice Guidelines | 2026-06-30 | Chris
3 | Governance | Vendor Brand Usage Agreement | Agreement template for vendor/partner brand usage | DOCX/PDF | Not Started |  | 2026-07-31 | Chris
3 | Governance | Brand Audit Checklist (Annual) | Annual checklist for auditing brand consistency | XLSX/PDF | Not Started |  | 2026-08-31 | Chris
3 | Governance | Asset Request Form | Form for internal teams to request branded assets | XLSX/PDF | Not Started |  | 2026-06-30 | Chris

## Summary Dashboard
FAI Brand Refresh - Template Audit Summary
SUMMARY BY TIER
Tier | Total Items | Not Started | In Progress | Existing/Needs Update | Complete
Tier 1 (Foundation) | 18 | 18 | 0 | 0 | 0
Tier 2 (Core Templates) | 36 | 34 | 0 | 2 | 0
Tier 3 (Extended Applications) | 35 | 35 | 0 | 0 | 0
TOTAL | 89 | 87 | 0 | 2 | 0
SUMMARY BY CATEGORY
Category | Total Items | Complete | In Progress | Existing/Needs Update | Not Started
Logo System | 6 | 0 | 0 | 0 | 6
Color System | 4 | 0 | 0 | 0 | 4
Typography | 4 | 0 | 0 | 0 | 4
Voice & Tone | 4 | 0 | 0 | 0 | 4
Publications | 6 | 0 | 0 | 1 | 5
Presentations | 4 | 0 | 0 | 1 | 3
Social Media | 7 | 0 | 0 | 0 | 7
Email / Newsletter | 5 | 0 | 0 | 0 | 5
Events | 9 | 0 | 0 | 0 | 9
Stationery | 5 | 0 | 0 | 0 | 5
Sub-Brand Guidelines | 6 | 0 | 0 | 0 | 6
Donor/Development Materials | 6 | 0 | 0 | 0 | 6
Swag & Merchandise | 7 | 0 | 0 | 0 | 7
Digital/Web | 6 | 0 | 0 | 0 | 6
Video/Motion | 5 | 0 | 0 | 0 | 5
Governance | 5 | 0 | 0 | 0 | 5

## Timeline View
Deadline | Tier | Category | Asset Name | Status | Dependencies
2026-02-27 | 2 | Publications | Print Booklet/Program Template | Existing/Needs Update | Typography;Logo System
2026-02-27 | 2 | Presentations | Master FAI Deck Template | Existing/Needs Update | Typography;Color System;Logo System
2026-03-15 | 1 | Typography | Typeface License Documentation | Not Started
2026-03-31 | 1 | Logo System | Primary Logo Files (SVG, PNG, EPS, AI) | Not Started
2026-03-31 | 1 | Logo System | Secondary/Alternate Mark | Not Started | Primary Logo Files
2026-03-31 | 1 | Color System | Color Specification Sheet | Not Started
2026-03-31 | 1 | Typography | Type Specimen Sheet | Not Started | Typeface License Documentation
2026-03-31 | 1 | Typography | Typography Hierarchy Reference Card | Not Started | Type Specimen Sheet
2026-03-31 | 2 | Publications | Web-Native Policy Paper Template | Not Started | Typography;Color System
2026-04-15 | 1 | Color System | Color Palette Files (ASE, CLR) | Not Started | Color Specification Sheet
2026-04-15 | 1 | Typography | Web Font Files | Not Started | Typeface License Documentation
2026-04-15 | 1 | Voice & Tone | Email Signature Standard | Not Started | Typography;Logo System
2026-04-15 | 2 | Presentations | Speaker One-Sheet/Bio Template | Not Started | Typography;Logo System
2026-04-15 | 2 | Social Media | Social Media Avatar & Profile Photo Specs | Not Started | Logo System
2026-04-15 | 2 | Email / Newsletter | Email Signature Template | Not Started | Typography;Logo System
2026-04-30 | 1 | Logo System | Logo Usage Guide Page | Not Started | Primary Logo Files
2026-04-30 | 1 | Color System | Accessibility Contrast Ratio Documentation | Not Started | Color Specification Sheet
2026-04-30 | 1 | Voice & Tone | Brand Voice Guidelines | Not Started
2026-04-30 | 1 | Voice & Tone | Boilerplate Copy Library | Not Started | Brand Voice Guidelines
2026-04-30 | 1 | Voice & Tone | Terminology Glossary | Not Started | Brand Voice Guidelines
2026-04-30 | 2 | Publications | Print Policy Brief Template | Not Started | Typography;Color System;Logo System
2026-04-30 | 2 | Presentations | Internal Meeting Deck Template | Not Started | Master FAI Deck Template
2026-04-30 | 2 | Email / Newsletter | The SCIF Newsletter Template | Not Started | Typography;Color System;Logo System
2026-04-30 | 2 | Email / Newsletter | Event Invitation Email Template | Not Started | Typography;Logo System;Color System
2026-04-30 | 2 | Email / Newsletter | Internal Announcement Email Template | Not Started | Typography;Logo System;Color System
2026-04-30 | 2 | Events | Event Program/Booklet Template | Not Started | Typography;Logo System;Event Branding Toolkit
2026-04-30 | 2 | Events | Name Badge Template | Not Started | Typography;Logo System
2026-04-30 | 2 | Events | Event Invitation (Digital - Luma) | Not Started | Typography;Logo System;Color System
2026-04-30 | 2 | Events | Event Invitation (Print) | Not Started | Typography;Logo System;Color System
2026-04-30 | 2 | Events | Table Tent/Place Card Template | Not Started | Typography;Logo System
2026-04-30 | 2 | Stationery | Letterhead Template | Not Started | Logo System;Typography;Color System
2026-04-30 | 2 | Stationery | Business Card Template | Not Started | Logo System;Typography
2026-04-30 | 2 | Stationery | Envelope Templates | Not Started | Logo System;Typography
2026-04-30 | 2 | Stationery | Note Card/Thank You Card Template | Not Started | Logo System;Color System;Typography
2026-04-30 | 2 | Stationery | Memo Template | Not Started | Typography;Logo System
2026-05-15 | 2 | Events | Step-and-Repeat/Photo Backdrop Template | Not Started | Logo System;Color System
2026-05-31 | 1 | Logo System | Sub-Brand Lockup Templates | Not Started | Primary Logo Files
2026-05-31 | 1 | Logo System | Favicon & App Icon Set | Not Started | Primary Logo Files
2026-05-31 | 1 | Logo System | Watermark Versions | Not Started | Primary Logo Files
2026-05-31 | 1 | Color System | Sub-Brand Color Extensions | Not Started | Color Specification Sheet
2026-05-31 | 2 | Publications | Print Research Report Template | Not Started | Typography;Color System;Logo System
2026-05-31 | 2 | Publications | Blog Post Style Guide | Not Started | Typography;Color System
2026-05-31 | 2 | Presentations | Webinar/Virtual Event Slide Template | Not Started | Master FAI Deck Template
2026-05-31 | 2 | Social Media | X/Twitter Post Templates | Not Started | Color System;Typography;Logo System
2026-05-31 | 2 | Social Media | LinkedIn Post Templates | Not Started | Color System;Typography;Logo System
2026-05-31 | 2 | Social Media | YouTube Thumbnail Template | Not Started | Color System;Typography;Logo System
2026-05-31 | 2 | Social Media | YouTube Channel Art | Not Started | Logo System;Color System
2026-05-31 | 2 | Social Media | Instagram Templates | Not Started | Color System;Typography;Logo System
2026-05-31 | 2 | Social Media | Podcast Cover Art Template (The Dynamist) | Not Started | Logo System;Color System
2026-05-31 | 2 | Email / Newsletter | Fundraising/Donor Email Template | Not Started | Typography;Logo System;Color System
2026-05-31 | 2 | Events | Event Branding Toolkit | Not Started | Logo System;Color System;Typography
2026-05-31 | 2 | Events | Event Signage Template Set | Not Started | Typography;Logo System;Color System
2026-05-31 | 2 | Events | Event Slide Template | Not Started | Master FAI Deck Template
2026-06-15 | 2 | Publications | Book/Publication Cover Template | Not Started | Typography;Color System;Logo System
2026-06-30 | 3 | Sub-Brand Guidelines | The Dynamist Podcast Identity Package | Not Started | Logo System;Color System;Podcast Cover Art Template
2026-06-30 | 3 | Donor/Development Materials | Thank You/Acknowledgment Letter Template | Not Started | Typography;Logo System
2026-06-30 | 3 | Governance | Brand Approval Request Form | Not Started | Voice & Tone
2026-06-30 | 3 | Governance | New Sub-Brand Proposal Template | Not Started | Brand Voice Guidelines
2026-06-30 | 3 | Governance | Asset Request Form | Not Started
2026-07-31 | 3 | Sub-Brand Guidelines | Reboot Conference Identity Package | Not Started | Logo System;Color System;Typography;Sub-Brand Lockup Templates
2026-07-31 | 3 | Sub-Brand Guidelines | Energy Imperatives Summit Identity Package | Not Started | Logo System;Color System;Typography;Sub-Brand Lockup Templates
2026-07-31 | 3 | Sub-Brand Guidelines | FAI Labs Identity Package | Not Started | Logo System;Color System;Typography;Sub-Brand Lockup Templates
2026-07-31 | 3 | Sub-Brand Guidelines | Policy Hackers Identity Package | Not Started | Logo System;Color System;Typography;Sub-Brand Lockup Templates
2026-07-31 | 3 | Donor/Development Materials | Donor One-Pager Template | Not Started | Typography;Logo System
2026-07-31 | 3 | Donor/Development Materials | Grant Proposal Cover Template | Not Started | Typography;Logo System
2026-07-31 | 3 | Digital/Web | Website Redesign Brief | Not Started | Logo System;Color System;Typography
2026-07-31 | 3 | Digital/Web | Open Graph/Social Sharing Image Template | Not Started | Logo System;Color System;Typography
2026-07-31 | 3 | Digital/Web | 404 Page Design | Not Started | Logo System;Color System;Typography
2026-07-31 | 3 | Digital/Web | QR Code Branded Template | Not Started | Logo System;Color System
2026-07-31 | 3 | Governance | Vendor Brand Usage Agreement | Not Started
2026-08-31 | 3 | Sub-Brand Guidelines | Sub-Brand Identity Creation Template | Not Started | Logo System;Color System;Typography
2026-08-31 | 3 | Donor/Development Materials | Annual Report Template | Not Started | Typography;Logo System;Color System
2026-08-31 | 3 | Donor/Development Materials | Case for Support/Prospectus Template | Not Started | Typography;Logo System;Color System
2026-08-31 | 3 | Donor/Development Materials | Impact Report Template | Not Started | Typography;Logo System;Color System
2026-08-31 | 3 | Swag & Merchandise | Sticker Designs | Not Started | Logo System;Color System
2026-08-31 | 3 | Swag & Merchandise | Apparel Templates | Not Started | Logo System;Color System
2026-08-31 | 3 | Swag & Merchandise | Tote Bag Template | Not Started | Logo System;Color System
2026-08-31 | 3 | Swag & Merchandise | Lapel Pin/Enamel Pin Design | Not Started | Logo System
2026-08-31 | 3 | Swag & Merchandise | Drinkware Template | Not Started | Logo System;Color System
2026-08-31 | 3 | Swag & Merchandise | Notebook/Padfolio Cover | Not Started | Logo System;Color System;Typography
2026-08-31 | 3 | Swag & Merchandise | Pen/Promotional Item Specs | Not Started | Logo System
2026-08-31 | 3 | Digital/Web | Web Component Style Guide | Not Started | Typography;Color System
2026-08-31 | 3 | Digital/Web | Loading/Transition Animations | Not Started | Color System
2026-08-31 | 3 | Video/Motion | Video Intro/Outro Bumper | Not Started | Logo System;Color System;Typography
2026-08-31 | 3 | Video/Motion | Lower Third Template | Not Started | Logo System;Color System;Typography
2026-08-31 | 3 | Video/Motion | Animated Logo | Not Started | Logo System
2026-08-31 | 3 | Video/Motion | Motion Graphics Style Guide | Not Started | Color System;Typography
2026-08-31 | 3 | Video/Motion | Podcast Video Template | Not Started | Logo System;Color System;Typography
2026-08-31 | 3 | Governance | Brand Audit Checklist (Annual) | Not Started